## Sheet1
Week 1 | 22-Oct - 27-Oct
Week 2 | 29-Oct - 3-Nov
Week 3 | 5-Nov - 10-Nov
Week 4 | 12-Nov - 17-Nov
Week 5 | 19-Nov - 24-Nov
Week 6 | 26-Nov - 1-Dec
Week 7 | 3-Dec - 8-Dec
Week 8 | 10-Dec - 15-Dec
Week 9 | 17-Dec - 19-Dec
Task Code | ** UI Components | Week Assigned
UI-1 | - Show status of an ancestor's Temple Work (2 Hours) | Week 7
UI-2 | - Provide ability to share an Ancetor's Temple Work (2 Hours) | Week 6
UI-3 | - Provide ability to accept an Ancestor's Temple Work (2 Hours) | Week 6
UI-4 | - Provide ability to view an Ancestor's Temple Work (4 Hours) | Week 6
UI-5 | - Provide ability to view assigned Temple Work for a user (3 Hours) | Week 7
UI-6 | - Provide ability to print assigned Temple Work for a user (2 Hours) | Week 7
UI-7 | - Provide ability to update assigned Temple Work for a user (4 Hours) | Week 7
UI-8 | - Provide ability to delete assigned Temple Work for a user (2 Hours) | Week 7
** Client-Side Components
CL-1 | - Write function to upload Temple Work (2 Hours) | Week 5
CL-2 | - Write function to receive Temple Work (2 Hours) | Week 5
CL-3 | - Write function to report work performed for Temple Work (4 Hours) | Week 5
CL-4 | - Write function to delete Temple Work (2 Hours) | Week 5
** Server-Side Components
SV-1 | - Write function to create a Temple Ordinance Record (30 Minutes) | Week 1 | Complete
SV-2 | - Write function to receive Temple Work from the client (1 Hour) | Week 4
SV-3 | - Write function to upload a Temple Ordinance Record and Temple Work to File Storage (2 Hours) | Week 2
SV-4 | - Write function to retrieve a Temple Ordinance Record from File Storage (1 1/2 Hours) | Week 2 | Complete
SV-5 | - Write function to retrieve Temple Work from File Storage (2 Hours) | Week 2 | Complete
SV-6 | - Write function to update ordinance status of Temple Ordinance Record (1 Hour) | Week 4
SV-7 | - Write function to update assigned status of Temple Ordinance Record (1 Hour) | Week 4
SV-8 | - Write function to download Temple Work to the client (2 Hours) | Week 4 | Complete
** Design Components
DS-1 | - Design Temple Ordinance Record (1 Hour) | Week 1 | Complete
DS-3 | - Implement Objects for each of these designs (1 Hour) | Week 1 | Complete
DS-4 | - Design API calling structure (1 Hour) | Week 1 | Complete
DS-5 | - Implement API calling structure (1 Hour) | Week 2
DS-6 | - Design UI Components | Week 3
DS-7 | - Design Temple Ordinance Record and Temple Work storage and retrieval system (1 Hour) | Week 2 | Complete
DS-8 | Make Specification Document | Week 3